## Executive Summary
Vault / SafeVault implementation review — after PR #7
Review date | 2026-09-07 | Scope | Connected GitHub main branches
Finding | Conclusion | Status | Implication
VLT approved network | Ethereum mainnet only, chain ID 1 | CONFIRMED | PR #7 changed VLT policy and removed Sepolia deployment/preflight materials.
VLT deployment | Not deployed; no proxy, implementation, or tx recorded | BLOCKED | Do not configure a live VLT address or market the token as live.
SafeVault frontend network | Still supports chain IDs 1 and 11155111; defaults to Sepolia | RECONCILE | Frontend policy is not yet aligned with the new VLT authority policy.
SafeVault wallet capability | Phase 1 shell only; writes disabled | NEEDS BUILD | Add wallet connection, signing, reads, asset registry, and transaction monitoring.
RPC model | Read through RPC/indexer; sign through user wallet | RECOMMENDED | Backend may read and monitor, but must never receive or use VaultKeys.
Source links | Vault Coin PR #7 | SafeVault runtime
Important boundary | Mainnet-only is confirmed for the VLT repository. It is not yet true of the SafeVault frontend configuration.
Note on A1: Prepared from GitHub repositories connected in this conversation. Verify live state before deployment.

## Repository Findings
Repository | Visibility | Current role | Reusable material | Missing for Vault | Review status | Source
safevault-deployment | Private | Frontend foundation | React/TypeScript/Vite, runtime validation, Docker/nginx, tests | Wallet connection, RPC reads, signing, asset registry, backend, history | Needs build | https://github.com/blackvault-opps/safevault-deployment
SafeVault_deploy-repo | Public | Product/security framework | Self-custody principles, VaultKey boundary, transaction flow | Executable wallet implementation | Specification | https://github.com/blackvault-opps/SafeVault_deploy-repo
Blackvault-Public-Network-repo | Public | Ecosystem publication | Separation of SafeVault, VLT, rewards, affiliate, and payment systems | Application code | Documentation | https://github.com/blackvault-opps/Blackvault-Public-Network-repo
Vault-Coin-VLT-project | Public | Token protocol | Solidity contract, UUPS proxy, Foundry tests and local rehearsal | Mainnet deployment, verified address, independent audit, Vault integration | Mainnet policy only | https://github.com/blackvault-opps/Vault-Coin-VLT-project
Note on A1: Prepared from GitHub repositories connected in this conversation. Verify live state before deployment.

## Architecture Components
Component | Owner of authority | Vault responsibility | Allowed data flow | Forbidden data flow | Status | Implementation note
User wallet | User | Approve/reject signatures | Public address in; signature result out | Private key or seed phrase out | External dependency | MetaMask, Coinbase Wallet, Trust Wallet, Ledger, or compatible EVM wallet
Vault frontend | BlackVault product | Dashboard, review, send, receive, monitoring | Reads public data; requests wallet signatures | Silent signing; custody; hidden destination changes | Needs build | Use current React/Vite shell as starting point
RPC provider | Third-party / infrastructure | Read chain state, estimate gas, broadcast signed tx | Public JSON-RPC requests and signed transaction | Private key access | Needs configure | Prefer provider abstraction and fallback strategy
Vault backend | BlackVault product | Sessions, indexing, receipts, token metadata | Public address, tx hash, public chain data | Raw VaultKey, seed phrase, decrypted keystore | Not present | Non-custodial API; no signing service
Ethereum mainnet | Ethereum network | Canonical settlement layer | Transactions, balances, logs, contract state | Application-only balance authority | Authoritative | Chain ID 1 is the only approved VLT deployment network
VLT proxy | Authorized owner address | ERC-20 token behavior and controls | ABI calls and events through proxy address | Use implementation address as user token address | Not deployed | Integrations must use proxy after independently verified deployment
Note on A1: Prepared from GitHub repositories connected in this conversation. Verify live state before deployment.

## Transaction Workflow
Step | Stage | User action | Vault action | Blockchain / wallet action | Status | Failure cases to test
1 | Connect | Approve public address connection | Create read-only session | Wallet exposes address | Needs build | Wrong account, wrong network, disconnect
2 | Read | View assets | Query RPC/indexer | Returns balances and history | Needs build | RPC timeout, stale index, unsupported token
3 | Prepare | Enter asset, destination, amount | Validate and simulate | Wallet not yet asked to sign | Needs build | Invalid address, insufficient balance, wrong chain
4 | Review | Inspect transaction summary | Show network, contract, destination, amount, fee | User decides whether to continue | Needs build | Contract mismatch, fee spike, suspicious token
5 | Sign | Approve or reject in wallet | Wait for signature result | User wallet signs or rejects | Needs build | User rejection, wallet locked, hardware failure
6 | Broadcast | No additional custody action | Submit signed transaction and store hash | Ethereum accepts or rejects tx | Needs build | Nonce conflict, gas too low, reverted call
7 | Monitor | View status | Poll/index receipt and show explorer link | Pending → confirmed/failed | Needs build | Reorg, dropped tx, replacement transaction
Note on A1: Prepared from GitHub repositories connected in this conversation. Verify live state before deployment.

## Network Policy
Surface | Network | Chain ID | Deployment / runtime role | Current evidence | Decision | Required action
VLT repository policy | Ethereum mainnet | 1 | Only approved pre-deployment network | PR #7 README and deployment guide | Confirmed | Keep as authoritative network policy
VLT deployment script | Local Foundry chain | 31337 | Local rehearsal only | Script rejects any other chain | Allowed for local tests | Do not treat as live deployment entry point
VLT Sepolia workflow | Sepolia | 11155111 | Former preflight/deployment path | Removed by PR #7 | Removed | Do not restore without an explicit policy decision
SafeVault runtime | Ethereum mainnet | 1 | Supported frontend chain | Supported in runtime.ts | Keep | Make mainnet the only production target
SafeVault runtime | Sepolia | 11155111 | Current default and supported chain | Still present in runtime.ts/.env.example | Mismatch | Separate local mock/test profile or remove from production config
VLT contract | Ethereum mainnet | 1 | Future production token deployment | No proxy or implementation address | Not deployed | Create verified deployment record before enabling VLT
Note on A1: Prepared from GitHub repositories connected in this conversation. Verify live state before deployment.

## Security and Gates
ID | Gate | Why it matters | Evidence required | Owner | Status | Exit condition
G1 | Reconcile production chain policy | Avoids shipping a Sepolia-default app against mainnet-only VLT policy | Updated runtime, environment profiles, tests, docs | SafeVault team | Open | Production config allows chain ID 1 only
G2 | Wallet connection threat model | Defines what Vault can request and what it cannot access | Threat model and user disclosures | SafeVault team | Open | No key material crosses app/backend boundary
G3 | Public RPC strategy | RPC providers can fail, censor, rate-limit, or return stale data | Provider abstraction, fallback policy, health checks | Platform team | Open | Reads remain verifiable and broadcast path is explicit
G4 | VLT deployment record | No token integration should rely on an unverified address | Chain ID, proxy, implementation, tx hash, bytecode, ABI | Token governance | Blocked | Independently verified mainnet proxy exists
G5 | Independent security review | Local tests do not establish production safety | Wallet app and smart-contract review reports | Governance | Blocked | Critical findings remediated and accepted
G6 | Transaction UX tests | Users need protection from wrong network, address, fee, and contract errors | Automated and manual test evidence | SafeVault team | Open | All failure states are visible and recoverable
Note on A1: Prepared from GitHub repositories connected in this conversation. Verify live state before deployment.